## Master
Tasks | Time (in hours)
Watch how to create a login page with javascript tutorial | 1
Create/code landing page with options of either (login or create new account) (Frontend) | 3
For create new account, create second page to create new account with options of either fitbit or gmail) (Frontend) | 2
For create new account, (fitbit) redirect user to fitbit signin (Frontend) | 1
For create new account, (fitbit) link api to application, select information we want from fitbit user | 2.5
For create new account, (gmail) create page for user to create profile(password and username) | 2
For create new account, (gmail) build requirements for password | 0.5
Create page for sign in (if not creating a new account) (Frontend) | 1
Check if username taken | 0.5
Verify if user input is valid | 0.5
Build 'remember me' option | 2
Build a database schema for user login information | 4
Store valid user login info in db | 0.5
Final Debugging | 5
Total | 25.5

## Maha
Tasks | time (hrs)
Create landing page | 2
Create frontend form for general sign in | 1
redirect to message for incorrect email/password | 0.5
verify username and password | 1
redirect to sign up for no username found | 0.3
Create form for sign up | 0.5
Build DB for saving user info | 2
match username with usernames in DB to check if taken | 1
Total | 8.3

## Kiril
Create the basic layout of the main log in page. 1 hr
Add buttons for ‘login’ and ‘create a new account’. 0.5 hr
Link the buttons to the pages they should take the user to when he/she clicks on them. 0.5 hr
Create a new page that gives the option to either sign in through fitbit or sign in through email for when the user clicks ‘create a new account’ on the first page. 2 hr
Add buttons for ‘sign in through fitbit ‘ and ‘sign in through email’. 0.5 hr
Create a database to store user log-in info. 4 hr
Link buttons to the pages they should take you to when you click on them. 0.5 hr
Let the user create username and password. 3 hr
Output appropriate messages when username and password don’t meet requirements. 1 hr
Debug. 5 hr

## Kyle
Requirments for succcessful log in
Make form |  | 1.5 hours
Sign in with fit bit |  | 1.5 hour
Create account with email |  | 1 hour
Sign in with email |  | 2 hours
save user account info |  | 1 hour +db
create username |  | 30 minutes
check if username taken |  | 2 hours
save username to database |  | 30 minutes w/ database
remember button for automatic signin |  | 2 hours
create database somewhere |  | 4 hours
:30 | 1:00 | 1:30 | 2:00 | 2:30 | 3:00 | 3:30 | 4:00 | 4:30 | 5:00 | 5:30 | 6:00 | 6:30 | 7:00
Create database | Create database | Create database | Create database | Create database | Create database | Create database | Create database | Create Acount | Create Acount | Create Acount | Create Acount | Create Acount | Create Acount
Create page for inputs | Create page for inputs | Create page for inputs
|  |  | Create username | Create username
[8 empty] | Check if UN taken | Check if UN taken | Check if UN taken | Check if UN taken
[8 empty] | SIgn in with fitbit | SIgn in with fitbit | SIgn in with fitbit | SIgn in with fitbit | SIgn in with fitbit | SIgn in with fitbit
[6 empty] | Auto SI | Auto SI
[8 empty] | Sign in with email | Sign in with email | Sign in with email | Sign in with email | Sign in with email | Sign in with email

## Katelyn
Task | Time (in hours)
Watch how to create a login page with javascript tutorial | 1 | https://www.youtube.com/watch?v=Gl5SI82A7SQ
Create/code opening page with options of either (login or create new account) | 1
-For create new account, create second page to create through (fitbit or gmail) | 2
-For create new account, (fitbit) link api to application, select information we want from fitbit user | 2
-For create new account, (fitbit) create page for user to sign in | 1
-For create new account, (gmail) create page for user to create profile(password and username) | 1
-For create new account, (gmail) build requirements for password | 0.5
build user profile database to store information | 2
- For creating new account, (gmail and fitbit) build 'remember me' option | 1

## Kaela
Tasks: | Time:
Build a database schema for user login information | 0.5 hours
Create frontend for user to input information | 4 hours
Implement Fitbit Oauth login | 1.5 hours
Verify if user input is valid | 1 hour
Store valid user login info in db | 1 hour